## GFO
Home Means Nevada Awards Status 09.21.2023
Total Proposed Funding (MM) | 499000000 | 100%
Actual Funding Provided / Proposed (MM) | 495956564.83 | 99.39% |  | Agreement Executed | Funds obligated and projects breaking ground, commencing rehab and/or deploying funds for home repair / downpayment assistance
Total Obligated (MM) | 226560998.83 | 45.68% |  | Documents in Final Review | Anticipate executed agreements and/or finance closings in next 1-3 months
Total Expended (MM) | 31024866.24 | 6.256% |  | Discussions Ongoing | Draft documents under review and negotiation by NHD and Subrecipient with anticipated obligation of funds April 2024
NEW DEVELOPMENT
Project Name | Organization Name | Service Area | Proposed Funding Award(MM) | Actual Funding Provided / Proposed (MM) | Agreement Status | Obligated Funds 9.21.23 (MM) | HMNI Funding Expended 9.21.23 (MM) | % HMNI Funding Expended per Project 9.21.23
WHA #2 | Washoe Housing Authority | Carson City | 5.5 | 5500000 | Agreement Executed | 5500000 | 351809.2 | 6.397%
Ridge at Sun Valley | Ulysses Development LLC | Reno | 28.5 | 28500000 | Agreement Executed/Financing Closed | 28500000 | 16574762 | 58.16%
Old Rose Gardens | Southern Nevada Regional Housing Authority | NLV | 10 | 10000000 | Discussions Ongoing
Stewart Pines 1,2,3 | NV Hand | LV | 4.7 | 4700000 | Discussions Ongoing
Buena Vista Springs III | NV Hand | NLV | 4.7 | 4700000 | Discussions Ongoing
Buffalo & Cactus | NV Hand | Clark County | 0 | 8100000 | Financing Due to Close October
Golden Rule Senior Apartments Phase II | Neighborhood Housing Services of Southern Nevada, Inc. | LV | 9 | 9000000 | Discussions Ongoing
Hawk View Apts | Reno Housing Authority | Washoe County | 25 | 10000000 | Discussions Ongoing
Dick Scott Manor 1 | Reno Housing Authority | Washoe County | 1.5 | 1500000 | Agreement Executed | 1500000 |  | 0%
Boulder & Gibson | NV Hand | Henderson | 31.5 | 31500000 | Discussions Ongoing
Pinyon Apartments | Lincoln Avenue Capital | Reno | 10.6 | 13600000 | Agreement Executed/Financing Closed | 13600000 |  | 0%
Line Drive Apts | Accessible Space | Reno | 15.8 | 15800000 | Documents in Final Review
Eagles Landing Phases 1-4 | Northern Nevada Community Housing Resource Board | Carson City | 39.4 | 39400000 | Agreement Executed | 36885934 | 1992343.86 | 5.401%
28th & Sunrise | Southern Nevada Regional Housing Authority | LV | 23.8 | 10500000 | Discussions Ongoing
South Nellis Permanent Supportive Housing | Coordinated Living of Southern Nevada / Ovation | Clark County | 6 | 18000000 | Discussions Ongoing
Duncan & Edwards | Southern Nevada Regional Housing Authority | LV | 10.5 | 10500000 | Discussions Ongoing
Pebble & Eastern | Coordinated Living of Southern Nevada / Ovation | Clark County | 22.3 | 0 | Withdrawn
Raiders Way | RISE Residential | Henderson | 15.7 | 15700000 | Discussions Ongoing
Marvel Wy | The Empowerment Center | Reno | 16.3 | 16300000 | Agreement Executed | 16300000
PuraVida Senior Housing | Foresight Housing Partners | NLV | 19.7 | 19700000 | Documents in Final Review
1800 Threlkel St CARES Campus | Washoe County | Reno | 21.9 | 21900000 | Agreement Executed | 21900000
Blind Center of NV | Blind Center of NV | Clark County | 15 | 15000000 | Agreement Executed/Financing Closed | 15000000 |  | 0%
Marion D Bennett Sr Plaza | Southern Nevada Regional Housing Authority | LV | 16.3 | 16300000 | Discussions Ongoing
Decatur and Rome Family Apartments | Coordinated Living of Southern Nevada / Ovation | LV | 26 | 11500000 | Discussions Ongoing
Eddy House | Eddy House | Reno | 6.5 | 11000000 | Discussions Ongoing
Village on Sage St Expansion | Community Foundation of N NV/ Housing Land Trust | Reno | 5.7 | 5700000 | Agreement Executed/Financing Closed | 5700000 |  | 0%
Sierra Flats Phase II | Oikos Development | Carson City | 0 | 8300000 | Agreement Executed/Financing Closed | 8300000 |  | 0%
Vintage at Redfield | Greenstreet Development | Reno | 0 | 16950000 | Agreement Executed/Financing Closed | 16950000 | 3647271.5 | 21.52%
The Empowerment Center | The Empowerment Center | Reno | 0 | 12500000 | Discussions Ongoing
The Village at the Women's & Childrens Campus | WestCare Nevada Inc | Las Vegas | 0 | 5000000 | Discussions Ongoing
Totals |  |  | 391.9 | 397150000 |  | 170135934 | 22566186.56
Multifamily Preservation / Acquistion & Rehab
Project Name | Organization Name | Service Area | Proposed Funding Award(MM) | Actual Funding Provided / Proposed (MM) | Status | Obligated Funds 9.21.23 (MM) | HMNI Funding Expended 9.21.23 (MM) | % HMNI Funding Expended per Project 9.21.23
Janice Broooks Bay | Southern Nevada Regional Housing Authority | LV | 6.5 | 6500000 | Discussions Ongoing
Silverada Manor | Reno Housing Authority | Washoe County | 12 | 12000000 | Discussions Ongoing
Trembling leaves | Northern Nevada Community Housing Resource Board | Reno | 7 | 7000000 | Discussions Ongoing
4th & Sutro Streets - Hwy 40 | Volunteers of America Northern California Northern Nevada | Reno | 2.3 | 4300000 | Documents in Final Review
Stead Manor | Reno Housing Authority | Reno | 18 | 18000000 | Agreement Executed | 18000000
Metropolitan Gardens | Integra Property Group | Reno | 0.5 | 500000 | Discussions Ongoing
Sagebrush Place 1 Reno LIHTC | Integra Property Group | Reno | 1.7 | 1700000 | Discussions Ongoing
Pinewood Apts | Integra Property Group | Reno | 0.7 | 700000 | Discussions Ongoing
Sagebrush Place II | Integra Property Group | Reno | 0.4 | 500000 | Discussions Ongoing
Sierra Pointe / Grenada | Integra Property Group | LV | 1.2 | 1200000 | Discussions Ongoing
McGraw Ct | Reno Housing Authority | Washoe County | 3.5 | 2500000 | Agreement Executed | 2500000
Silver Sage Court | Reno Housing Authority | Washoe County | - | 1000000 | Documents in Final Review
Essex Manor | Reno Housing Authority | Washoe County | 1.5 | 1500000 | Agreement Executed | 1500000
Capital Improvements on 3 ASI | Accessible Space | Reno/Carson | 1 | 1000000 | Discussions Ongoing
Totals |  |  | 56.3 | 58400000 |  | 22000000 | 0
Home Ownership and Rehabilitation
Project Name | Organization Name | Service Area | Proposed Funding Award(MM) | Actual Funding Provided / Proposed (MM) | Status | Obligated Funds 9.21.23 (MM) | HMNI Funding Expended 9.21.23 (MM) | % HMNI Funding Expended per Project 9.21.23
Home Means Nevada Down Payment Assistance Program | Nevada Housing Division | Statewide | 7.5 | 7500000 | Funding in Process | 7500000 | 2520000 | 33.6%
Home Repair Program | Nevada Rural Housing Authority (NRHA) | Statewide | 7.6 | 7630071 | Agreement Executed | 7630071 |  | 0%
Home Means Nevada Rural Down Payment Assistance (DPA) Program | Nevada Rural Housing Authority (NRHA) | Rural | 2.5 | 2500000 | Agreement Executed | 2500000 | 240000 | 9.6%
Critical Home Repair | Rebuilding Together Southern Nevada | Clark | 2 | 2000000 | Agreement Executed | 2000000 | 297185.85 | 14.86%
Fall Prevention Program | Rebuidling Together Southern Nevada | Clark | 3 | 3000000 | Agreement Executed | 3000000 |  | 0%
Jefferson North Project | Habitat for Humanity Las Vegas, Inc | Clark | 1.5 | 1500000 | Discussions Ongoing |  |  | 0%
Down Payment Assistance | Rural Nevada Development Corporation | Rural | 1 | 962500 | Agreement Executed | 962500 |  | 0%
Housing Rehabilitation | Rural Nevada Development Corporation | Rural | 0.7 | 687500 | Agreement Executed | 687500 |  | 0%
Home Means Nevada Safe and Healthy Housing Program | Rebuilding Together Northern Nevada | Washoe | 3 | 3000000 | Agreement Executed | 3000000 |  | 0%
Totals |  |  | 28.8 | 28780071 |  | 27280071 | 3057185.85
Land Acquisition
Organization Name |  | Service Area | Proposed Funding Award(MM) | Actual Funding Provided / Proposed (MM) | Status | Obligated Funds 9.21.23 (MM) | HMNI Funding Expended 9.21.23 (MM) | % HMNI Funding Expended per Project 9.21.23
City of Sparks |  | Sparks | 1 | 1000000 | Documents in Final Review |  |  | 0%
City of North Las Vegas |  | North Las Vegas | 10 | 0 | Withdrawn
Churchill County |  | Fallon | 1.7 | 1700000 | Agreement Executed | 1743500 |  | 0%
Nevada Rural Housing Authority |  | Winnemucca | 4.8 | 4626493.83 | Agreement Executed/Financing Closed | 4626493.83 | 4626493.83 | 100%
Reno Housing Authority |  | Reno | 2.2 | 1425000 | Discussions Ongoing |  |  | 0%
Reno Housing Authority |  | Reno |  | 775000 | Agreement Executed | 775000 | 775000 | 100%
Nevada Hand |  | Henderson | 2.1 | 2100000 | Discussions Ongoing |  |  | 0%
Totals |  |  | 21.8 | 11626493.83 |  | 7144993.83 | 5401493.83
Totals For HMNI |  |  | 498.8 | 495956564.83 |  | 226560998.83 | 31024866.24